Project Name

Phase Plan - Project Closure

Document History

| Version | Author | Date | Changes |
| --- | --- | --- | --- |
| 0.1 | Neville Turbit | 1 Feb 09 | First draft |

Table of Contents

Current Status	3

Work Required	3

Resources	3

Schedule	4

Milestones	4

Risks or Issues	5

Cost	5

# Current Status

Explain the current status of the project.

Example:

The new application has been handed over to the Business to use and maintain.  We have engaged an external consultant to carry out a PIR and are ready to proceed.

# Work Required

Identify the work required in the phase.  Using a Work Breakdown Structure (WBS) is a useful approach.

Example:

- Prepare for Phase

  - Identify work required

  - Identify existing processes that may be included

- Carry out the PIR

  - Survey

  - Interviews

  - Workshops

  - Report

  - Allocate Actions

- Close down the project

  - Archive documents

  - Close or dispose of facilities and equipment

- Produce Report

- Close Project

# Resources

List the skills required in the project and who might be involved in the next phase.  If a resource name is not available, just identify the skills.

Example:

| Role | Skills | Nominee |
| --- | --- | --- |
| Project Manager | Plan the phase Clean up documentation | P. Manager |
| External Consultant | Carry out PIR Produce report |  |
| Sponsor | Provide the money for, and executive support to the project Accept the report |  |

# Schedule

The schedule does not necessarily need to be a Gantt chart.  If a Gantt chart is prepared, attach it to the report.  The following example would suffice.  It should relate to the WBS.  You should also indicate when the phase will start and when it will end.

Example:

Phase Duration:  1 June to 20 June

| Activity | Work | Start | Finish |
| --- | --- | --- | --- |
| Prepare for Phase | 2 days | 1 June | 3 June |
| Carry out PIR | 2 days | 2 June | 6 June |
| Produce Report | 5 days | 7 June | 14 June |
| Etc. |  |  |  |

# Milestones

If the Phase is going to take a few weeks to complete, identify Milestones that will determine if the phase is on track.  As a generalisation there should be a milestone each week or at least every two weeks.

Example:

| Milestone | Date |
| --- | --- |
| Interviews planned and scheduled | 6 June |
| Interviews completed | 14 June |
| Etc. |  |

# Risks or Issues

If there are any impediments to the phase being successfully completed, they should be identified.  Once identified, it should be clear how they are to be handled to minimise impact.

| Risk or Issue | Action |
| --- | --- |
| Unclear where documents are to be stored | Discuss with PMO |
| Several key people have left the organisation | Arrange interviews out of hours by phone. |
| Etc. |  |

# Cost

Identify the cost of completing the phase.

Example:

Cost involved will be the cost of a Project Manager for 8 days.  At our standard IT charge out rate this is $.....