## Data Cleanup Plan
Data Cleanup Plan
Number | Data | Reason | Correction Method | Number | Assigned To | Est. Time (Days) | Percent Complete | Remaining Time (Days) | Est. Completion
|  | I=Incorrect M=Missing R=Reformat N=New O=Other | M=Manual S=System
1 | Missing names | Missing | Manual | 325 | KK | 2 | 40% | 1.2 | 2008-06-01
2 | Incorrect phone number format | Reformat | Manual | 1700 | AA | 4.5 | 10% | 4.05 | 2008-08-12
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| TOTAL |  |  |  |  | 6.5 | 19.23% | 5.25
|  | Incorrect | Manual
|  | Missing | System
|  | Reformat | Other
New
Other