## Resource Career Path
Resource Career Path
Resource Name | Contract or Permanent | Previous Role | Post Project Company Plans | Resource Comments | Actions | Responsible | Due Date | Resolved | Comments
Bill Smith | Contract | N/A | Contract conclude after Go Live. Approx end March | As expected |  |  |  | Yes
Karen James | Permanent | A/P Supervisor | Possibly move to another branch in the same role | Karen is not interested in moving to another branch. Has requested she go back to her old role. | Discuss her previous role with the A/P Mgr and see if we can relocate her to that role | HR Mgr | 2008-11-12 | No | The person currently filling Karen's previous role may be agreeable to be moved to another branch.
[5 empty] | Meet again with Karen to discuss outcome of discussion with A/P Mgr | Project Mgr and HR Mgr | 2008-11-19
Contract | Yes
Permanent | No