## Instructions
RACI Converter - Instructions
- | Enter data on RACI worksheet
- | Press "Update Roles" to sort into roles on the "Roles" sheet
- | On the "RACI" worksheet enter names in row 1 starting at cell B1
- | On the "RACI" worksheet enter responsibilities in Column B using the drop down list
- | Blank is a valid value for the responsibility
- | Do not delete lines. Only erase the contents. You can cut and paste.
| R=Responsible | A=Accountable | C=Consulted | I=Information
| The person/function who will do the work | The person/function that will be held accountable. “The buck stops here!” | The person/function that provides input. Two way communication. | The person/function that will be provided with this information. One way communication
| Principals | The following principals apply to the definition of roles and responsibilities.
· One person may perform more than one role
· Several people may fill the same role. For example the Business User role will apply to a number of people from different functional areas.
· In the RACI chart, only one person can be Responsible for each activity
· In the RACI chart only one person can be Accountable for each activity
· In the RACI chart those receiving information are only identified if they need the information to fulfill their role. If the information is only “to keep them in the loop” they are not identified as an “I”.

## RACI
RACI | Sponsor | Steering Committee | Project Manager | State Team | Data Conv .Team | Functionality Team | Training Team | UAT Team | Project Director
Provide direction and leadership to the project | A | R | C | I | I | I | I | I | C
Resolve issues regarding strategic direction | A | R | C | I | I | I | I | I | C
Approve the continuation of the project at gates | AR | C | C | I | I | I | I | I | C
Authorise funding for projects | A | C | C | I | I | I | I | I | C
Tracking costs | I | I | AR | C | C | I | I | I | I
Identify Benefits | A A: A; R R: C; C C: R; I I: C; I I: C
Ensure Senior Management are up to date with progress of the project | A | R | C | C | C | C | C | C | I
Develop and implement a communications plan and revise where necessary | A | C | R | C | C | C | C | C | I
Maintain open communication channels between projects | A | C | R | C | C | C | C | C | C
Determine Scope | A | I | R | C | C | C | C | C | C
Create a Risk Plan | A | I | R | C | C | C | C | C | I
Create Schedule | I | I | AR | C | C | C | C | C | I
Create a quality plan | I | I | AR | C | C | C
Undertake quality activities | A A: I; R R: AR; C C: C; C C: C; C C: C
Create a Test Plan |  |  | A | C | C | C | I | R
Undertake testing | I | I | A | C | C | C | I | R
Correct Errors | A: A; C: C; C: C; C: R | I
Provide Guidance on correction |  |  | A | R | C | I |  | C
Run reports | I |  | A | R | C | I |  | C
Run Conversions | I |  | A | C | R | C
Ensuring Corporate Governance Stds are applied | R | A | c | C | C | C | C | C | C
Manage risks, issues, assumptions, actions | I | I | A | c | c | R | c | C
Manage variation requests | A | C | R | C | C | C | C | c | C
Maintain the schedule | A | C | R | C | C | C | C | C
Manage resource allocation across projects | C | I | R | C | c | I | A | C | c
Manage dependencies across projects | C | I | R | C | c | I | A | C | c
Ensure consistency across projects | C |  | R | C | c | I | A | C | c
Identify resource requirements | I | I | C | C | C | C | I | C | AR
Provide sufficient resources to fix data | A | C | R | I | I | I | I | I | I
Allocating IT Resources | I | C | C | C | C | C | AR | C | C
Clean up errors | A | I | R | C | I | I | I | I | C
Set Readiness Criteria | A | C | R | C | C | C | C | I | C
Meeting Readiness Tests | A | I | R | C | C | C | C |  | C
A
R
AR
C
I

## Roles
Role | Responsibility | Activity
Sponsor | Accountable | Provide direction and leadership to the project
Resolve issues regarding strategic direction
Authorise funding for projects
Identify Benefits
Ensure Senior Management are up to date with progress of the project
Develop and implement a communications plan and revise where necessary
Maintain open communication channels between projects
Determine Scope
Create a Risk Plan
Manage variation requests
Maintain the schedule
Provide sufficient resources to fix data
Clean up errors
Set Readiness Criteria
Meeting Readiness Tests
| Accountable & Responsible | Approve the continuation of the project at gates
| Responsible | Ensuring Corporate Governance Stds are applied
| Consulted | Manage resource allocation across projects
Manage dependencies across projects
Ensure consistency across projects
| Informed | Tracking costs
Create Schedule
Create a quality plan
Undertake quality activities
Undertake testing
Run reports
Run Conversions
Manage risks, issues, assumptions, actions
Identify resource requirements
Allocating IT Resources
Steering Committee | Accountable | Ensuring Corporate Governance Stds are applied
| Responsible | Provide direction and leadership to the project
Resolve issues regarding strategic direction
Ensure Senior Management are up to date with progress of the project
| Consulted | Approve the continuation of the project at gates
Authorise funding for projects
Identify Benefits
Develop and implement a communications plan and revise where necessary
Maintain open communication channels between projects
Manage variation requests
Maintain the schedule
Provide sufficient resources to fix data
Allocating IT Resources
Set Readiness Criteria
| Informed | Tracking costs
Determine Scope
Create a Risk Plan
Create Schedule
Create a quality plan
Undertake testing
Manage risks, issues, assumptions, actions
Manage resource allocation across projects
Manage dependencies across projects
Identify resource requirements
Clean up errors
Meeting Readiness Tests
Project Manager | Accountable | Create a Test Plan
Undertake testing
Correct Errors
Provide Guidance on correction
Run reports
Run Conversions
Manage risks, issues, assumptions, actions
| Accountable & Responsible | Tracking costs
Create Schedule
Create a quality plan
Undertake quality activities
| Responsible | Identify Benefits
Develop and implement a communications plan and revise where necessary
Maintain open communication channels between projects
Determine Scope
Create a Risk Plan
Manage variation requests
Maintain the schedule
Manage resource allocation across projects
Manage dependencies across projects
Ensure consistency across projects
Provide sufficient resources to fix data
Clean up errors
Set Readiness Criteria
Meeting Readiness Tests
| Consulted | Provide direction and leadership to the project
Resolve issues regarding strategic direction
Approve the continuation of the project at gates
Authorise funding for projects
Ensure Senior Management are up to date with progress of the project
Identify resource requirements
Allocating IT Resources
State Team | Responsible | Provide Guidance on correction
Run reports
| Consulted | Tracking costs
Identify Benefits
Ensure Senior Management are up to date with progress of the project
Develop and implement a communications plan and revise where necessary
Maintain open communication channels between projects
Determine Scope
Create a Risk Plan
Create Schedule
Create a quality plan
Undertake quality activities
Create a Test Plan
Undertake testing
Correct Errors
Run Conversions
Ensuring Corporate Governance Stds are applied
Manage variation requests
Maintain the schedule
Manage resource allocation across projects
Manage dependencies across projects
Ensure consistency across projects
Identify resource requirements
Allocating IT Resources
Clean up errors
Set Readiness Criteria
Meeting Readiness Tests
| Informed | Provide direction and leadership to the project
Resolve issues regarding strategic direction
Approve the continuation of the project at gates
Authorise funding for projects
Provide sufficient resources to fix data
Data Conv .Team | Responsible | Run Conversions
| Consulted | Tracking costs
Identify Benefits
Ensure Senior Management are up to date with progress of the project
Develop and implement a communications plan and revise where necessary
Maintain open communication channels between projects
Determine Scope
Create a Risk Plan
Create Schedule
Create a quality plan
Undertake quality activities
Create a Test Plan
Undertake testing
Correct Errors
Provide Guidance on correction
Run reports
Ensuring Corporate Governance Stds are applied
Manage variation requests
Maintain the schedule
Identify resource requirements
Allocating IT Resources
Set Readiness Criteria
Meeting Readiness Tests
| Informed | Provide direction and leadership to the project
Resolve issues regarding strategic direction
Approve the continuation of the project at gates
Authorise funding for projects
Provide sufficient resources to fix data
Clean up errors
Functionality Team | Responsible | Correct Errors
Manage risks, issues, assumptions, actions
| Consulted | Ensure Senior Management are up to date with progress of the project
Develop and implement a communications plan and revise where necessary
Maintain open communication channels between projects
Determine Scope
Create a Risk Plan
Create Schedule
Create a quality plan
Undertake quality activities
Create a Test Plan
Undertake testing
Run Conversions
Ensuring Corporate Governance Stds are applied
Manage variation requests
Maintain the schedule
Identify resource requirements
Allocating IT Resources
Set Readiness Criteria
Meeting Readiness Tests
| Informed | Provide direction and leadership to the project
Resolve issues regarding strategic direction
Approve the continuation of the project at gates
Authorise funding for projects
Tracking costs
Provide Guidance on correction
Run reports
Manage resource allocation across projects
Manage dependencies across projects
Ensure consistency across projects
Provide sufficient resources to fix data
Clean up errors
Training Team | Accountable | Manage resource allocation across projects
Manage dependencies across projects
Ensure consistency across projects
| Accountable & Responsible | Allocating IT Resources
| Consulted | Ensure Senior Management are up to date with progress of the project
Develop and implement a communications plan and revise where necessary
Maintain open communication channels between projects
Determine Scope
Create a Risk Plan
Create Schedule
Ensuring Corporate Governance Stds are applied
Manage variation requests
Maintain the schedule
Set Readiness Criteria
Meeting Readiness Tests
| Informed | Provide direction and leadership to the project
Resolve issues regarding strategic direction
Approve the continuation of the project at gates
Authorise funding for projects
Tracking costs
Create a Test Plan
Undertake testing
Identify resource requirements
Provide sufficient resources to fix data
Clean up errors
UAT Team | Responsible | Create a Test Plan
Undertake testing
| Consulted | Ensure Senior Management are up to date with progress of the project
Develop and implement a communications plan and revise where necessary
Maintain open communication channels between projects
Determine Scope
Create a Risk Plan
Create Schedule
Provide Guidance on correction
Run reports
Ensuring Corporate Governance Stds are applied
Manage risks, issues, assumptions, actions
Maintain the schedule
Manage resource allocation across projects
Manage dependencies across projects
Ensure consistency across projects
Identify resource requirements
Allocating IT Resources
| Informed | Provide direction and leadership to the project
Resolve issues regarding strategic direction
Approve the continuation of the project at gates
Authorise funding for projects
Tracking costs
Provide sufficient resources to fix data
Clean up errors
Set Readiness Criteria
Project Director | Accountable & Responsible | Identify resource requirements
| Consulted | Provide direction and leadership to the project
Resolve issues regarding strategic direction
Approve the continuation of the project at gates
Authorise funding for projects
Maintain open communication channels between projects
Determine Scope
Ensuring Corporate Governance Stds are applied
Manage variation requests
Allocating IT Resources
Clean up errors
Set Readiness Criteria
Meeting Readiness Tests
| Informed | Tracking costs
Ensure Senior Management are up to date with progress of the project
Develop and implement a communications plan and revise where necessary
Create a Risk Plan
Create Schedule
Correct Errors
Provide sufficient resources to fix data