## Defect Log
Defect Log
No. | Name | Description | Date Raised | Raised By | Test Script | Refered to | Urgency |  |  |  | Date Returned | Status |  |  | Attachments (Hyperlinks)
[7 empty] | L | M | H | C |  | Repair | Testing | Accepted
Totals | [6 empty] | 1 | 2 | 1 | 0 |  | 2 | 1 | 1
1 | Postcode Error | Must enter a postcode. Some O/S addresses have no code. | 2008-02-01 | JJ | D1.1 | PP |  |  | X |  | 2008-02-03 |  |  | X
2 | Duplicate Name | Rejected the same name although it was a different person………………………. | 2008-02-01 | JJ | D1.4 | PP |  | X |  |  | 2008-02-04 | X
3 | Name field too small | Only permitted 15 chars. See client 12345 | 2008-02-01 | JJ | D1.6 | KK |  | X |  |  | 2008-02-05 | X
4 | Typo "Address 1" on Name screen | Screen has "Adress 1" | 2008-02-02 | HH | T3.5 | KK | X |  |  |  | 2008-02-05 |  | X